## Sheet1
S. No. | User Stories | Target Sprint | Assigned To | Status
Customer
1 | As a customer, I should be able to login/register to the hotel management system | Sprint 1 | Vipul Mishra | Done
2 | As a customer, i should be able to update my profile | Sprint 1 | Vipul Mishra | Done
3 | As a customer, I would like to choose my room type. (Single, Double or Deluxe) | Sprint 1 | Balraj Govindaraj | Done
4 | As a customer, I should be able to select the number of rooms and total number of guests | Sprint 1 | Balraj Govindaraj | Done
5 | As a customer, I would like to be able to book my room | Sprint 2 | Vipul Mishra | Done
6 | As a customer, I should be able to select the payment type. (Cash or Card) | Sprint 2 | Vipul Mishra | Done
7 | As a customer, I should get a confirmation of reservation | Sprint 2 | Balraj Govindaraj | Done
8 | As a customer, I would like to call for service/maintenance and request different types of services and select the time of service | Sprint 2 | Balraj Govindaraj | Done
9 | As a customer, I would like to submit online request for service/maintenance and select the time of service | Sprint 2 | Balraj Govindaraj | Done
Employee
| As an employee, I should be able to login to the hotel management system. | Sprint 1 | Yuheng Chen | Done
| As an employee, I should be able to see the list of rooms with service requests types and time requested. | Sprint 1 | Yuheng Chen | IN PROGRESS
| As an employee, I should be able to assign the service request to myself. | Sprint 1 | Tianyang Lin | IN PROGRESS
| As an employee, I should be able to mark the service requests as completed for rooms once the service request is completed. | Sprint 1 | Tianyang Lin | IN PROGRESS
Manager
| As a manager, I should be able to login to the hotel management system. | TBD | Vipul Mishra | Done
| As a manager, I should be able to see Available and Not available room types. | TBD | Vipul Mishra | Done
| As a manager ,I should able to adjust the Booking fare of the Room. | TBD | Yuheng Chen | Done
| As a manager, I should be able to change/update reservation. | TBD | Balraj Govindaraj | IN PROGRESS
| As a manager, I should able to process cash customer payment and check them out. | TBD |  | NEW
| As a manger, I should be able to view all pending and completed service requests. | TBD |  | NEW
** TBD - To Be Discussed